## Sheet1
FACILITY | LOG DATE | MODULE | PROBLEM DESCRIPTION | Support Given/Solution Provided | STATUS | COMPLETION DATE
MARIAN MEDICAL CENTRE | 2022-10-05 | INVENTORY | Error while uploading stock take catalogue for a specific store |  | DONE
MARIAN MEDICAL CENTRE | 2022-10-11 | INVENTORY | Error when doing store requstions | We went through the inventory module, under the storage areas we merged the duplicate items in the respective stores. | DONE | 2022-10-11
KWA NG'ANG'A MEDICAL CENTRE | 2022-10-18 | PHARMACY | A drug could not appear. | Took the provider through the Inventory module, confirmed the drug was not in the on the product catalogue, since it was a new drug. we added a new item in the product catalogue and the added it to the respective store(pharmacy store) on the add item action tag. | DONE | 2022-10-18
MARIAN MEDICAL CENTRE | 2022-10-25 | FINANCE | Error when servicing a petty cash request. |  | DONE
MARIAN MEDICAL CENTRE | 2022-10-27 | CASHIER | Payment module not posting invoices for payment. |  | DONE
MARIAN MEDICAL CENTRE | 2022-10-27 | FINANCE | Cannot settle invoices using created bank accounts |  | DONE
MARIAN MEDICAL CENTRE | 2022-10-27 | SYSTEM ADMIN | Cannot assign action approvers |  | DONE
MEDIPOINT MEDICAL CENTRE | 2022-11-04 | LABORATORY | Adding a new lab test. | Took the lab tech through the laboratory module. We activated the test in the test catalogue and linked it with the corresponding price list item price | DONE | 2022-11-04
ISIOLO CENTRAL MEDICAL CENTRE | 2022-10-29 | SYSTEM ADMIN | Cannot assign action approvers |  | DONE
ISIOLO CENTRAL MEDICAL CENTRE | 2022-11-02 | LABORATORY | Too many pending lab tests. System to try and hide them |  | DONE
MEDIPOINT MEDICAL CENTRE | 2022-11-02 | LABORATORY | Double letterhead on the lab test print-out. |  | DONE
KWA NG'ANG'A MEDICAL CENTRE | 2022-11-15 | NURSE | ANC treatment form is not comprehensive for the clinic. |  | PENDING
KATHATHANI MEDICAL CENTRE | 2022-11-15 | REPORTS | Weekly lab report to the MOH not available. |  | PENDING
MEDIPOINT MEDICAL CENTRE | 2022-11-19 | CASHIER | Users cannot reverse an erroneous entry. |  | DONE
ISIOLO CENTRAL MEDICAL CENTRE | 2022-11-26 | DOCTOR | Treatment form not opening for certain patients. |  | DONE
Bridging Outpatient Centre - P.Koome | 2022-11-28 | Inventory | Drugs keep disappearing | Took the provider through the Inventory module, Confirmed the drug(s) were on the product catalogue, Checked their stock level on storage area and found the drug(s) were 0.0, leading to the "disappearance" since the system is configured to not display drug(s) that hav zero stock level. | Done | 2022-11-28
MEDIPOINT MEDICAL CENTRE | 2022-12-01 | PHARMACY | display age
MEDIPOINT MEDICAL CENTRE | 2022-11-30 | DOCTOR | deleting another doctors encounter eg diagnosis | the developer added a new update to restrict users from deleting other users encounters | done | 2022-11-30
MEDIPOINT MEDICAL CENTRE | 2022-12-02 | PATIENT REGISTER | Could not queue a self request patient | took the administrator through the patient register module and refreshed on the steps taken to queue a direct service patient. | done | 2022-12-02
ISIOLO CENTRAL MEDICAL CENTRE | 2022-12-08 | CASHIER | no invoice item to pay against | currently make use of the debtors tab as the developer gets a different approach to mitigate the problems | DONE | 2022-12-14
MEDIPOINT MEDICAL CENTRE | 2022-12-09 | CASHIER | no invoice item to pay against | currently make use of the debtors tab as the developer gets a different approach to mitigate the problems | DONE | 2022-12-14
KWA NG'ANG'A MEDICAL CENTRE | 2022-12-20 | INVENTORY | had a challenge moving an item from one store to the other | Took the client through a refreshers class where we added a new item to a given store. we also went through the store requisition process. | DONE | 2022-12-20
ISIOLO CENTRAL MEDICAL CENTRE | 2022-12-28 | CASHIER | Clarification on debtors tab | took the adminstrator trough the cashier module to clear any knowledge gaps | DONE | 2022-12-28
MARIAN MEDICAL CENTRE | 2023-01-09 | SARAMED | support training for new employees(receptionist,accountant and a clinical officer) | scheduled a virtual meeting and facilitated the training for the new staff. | DONE | 2023-01-09
ISIOLO CENTRAL MEDICAL CENTRE | 2023-01-11 | CASHIER | no invoice item to pay against | an update was pushed by developer to correct the situation | done | 2023-01-11
MARIAN MEDICAL CENTRE | 2023-01-11 | FINANCE | creating new price packages | guided the accountant how to create new pricing packages, editing prices of existing packages | done | 2023-01-11
MARIAN MEDICAL CENTRE | 2023-01-13 | INVENTORY | clarification on recieving goods purchased | refreshed the inventory and finance module with the admin | DONE | 2023-01-13
KWA NG'ANG'A MEDICAL CENTRE | 2023-01-18 | INVENTORY | refreshers class on store | went through the inventory module with the provider | DONE | 2023-01-18
ISIOLO CENTRAL MEDICAL CENTRE | 2023-01-21 | DOCTOR | category was not available | uploaded the 705a and 705b file | DONE | 2023-01-24
Bridging Outpatient Centre | 2023-01-24 | INVENTORY | stock level not reducing after sale |  | DONE | 2024-02-10
JEKIM MEDICAL CENTRE | 2023-01-28 | SYSTEM ADMIN | needed clarification on exclusion list | took the assistant admin through the module | DONE | 2023-01-28
JEKIM MEDICAL CENTRE | 2023-01-30 | FINANCE | Adjusting the pricing packages for insurance. | took the admin through the cashier and finance module | DONE | 2023-01-30
MEDIPOINT MEDICAL CENTRE | 2023-02-03 | PATIENT REGISTER | experiencing an error when trying to use the doctors module,nurse module or view queued patients | the developer run a script to correct the error they hada made by changing the insurance schemes. | DONE | 2023-02-03
MARIAN MEDICAL CENTRE | 2023-02-03 | INVENTORY | items purchased are received in multiples | configuration corrected causing the bug | DONE | 2023-02-08
JEKIM MEDICAL CENTRE | 2023-02-03 | FINANCE | error when trying to service a petty cash request | added Service pettycash payment request approval action | DONE | 2023-03-17
KWA NG'ANG'A MEDICAL CENTRE | 2023-02-13 | INVENTORY | refreshers class on placing a purchase order and receiving the items in the system | took the admin through the inventory and finance module | DONE | 2023-02-13
KWA NG'ANG'A MEDICAL CENTRE | 2023-02-14 | SYSTEM ADMIN | no approval actions items | uploaded the approvers actions item list. | DONE | 2023-02-14
JEKIM MEDICAL CENTRE | 2023-03-03 | FINANCE | create a way to capture mvc code when queing a patient. claim schedule to capture the month and datestamp of when the patients is queued.
MARIAN MEDICAL CENTRE | 2023-03-12 | INVENTORY | challenge receiving drugs in the system i.e, drug successfully received but it doesnt adjust the stock level in the receiving stores.
MARIAN MEDICAL CENTRE | 2023-03-16 | PATIENT REGISTER | experiencing an issue trying to queue a patient(child) sharing a phone number with another patient(parent) | developer corrected the check that restricted queuing patients with the same phone no. only the ID no is unique | DONE | 2023-03-16
Bridging Outpatient Centre | 2023-03-16 | PATIENT REGISTER | experiencing an issue trying to queue a patient(child) sharing a phone number with another patient(parent) | developer corrected the check that restricted queuing patients with the same phone no. only the ID no is unique | DONE | 2023-03-16
MEDIPOINT MEDICAL CENTRE | 2023-03-27 | INVENTORY | challenge adding a new item, create a purchase order and make a store requistion | took the client through the inventory module, creating purchase orders and receiving drugs. also covered the store requisition process. | DONE | 2023-03-27
bridging Outpatient Centre | 2023-03-30 | PATIENT REGISTER | double entries when registering a new patient | took the provider through the merging process | DONE | 2023-03-30